## Sheet1
Sr. No | Activities | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective 1 : Constitute and strengthen institutional mechanisms in mountain states involving a diverse range of stakeholders working towards mountain development
Create a database of individuals and institutions working on climate change, disaster risk reduction and agriculture and mountain livelihoods | bar: 2017 Q1 to 2017 Q2
Co-opt with individuals and institutions working on the above thematic areas | bar: 2017 Q1 to 2017 Q3
Establish sustainable development forums (SDF) in each IHR state | bar: 2017 Q1 to 2017 Q2
Strengthen existing sustainable mountain development forums (SDF) in each IHR state | bar: 2017 Q1 to 2017 Q2
Organise conferences & workshops for youth in Himalayan region | bar: 2017 Q2; 2018 Q2; 2019 Q2; 2020 Q2
Organise conferences & workshops bringing together women working across different sectors | bar: 2017 Q3; 2018 Q3; 2019 Q3; 2020 Q3
Objective 2: Carry out focused and evidence-based research to consolidate knowledge and foster practices for economically, socially and ecologically sound development relevant to mountain resource management in the Indian Himalayan Region
Collect secondary data available online on climate change, disaster risk reduction (DRR), mountain Livelihoods, gender | bar: 2017 Q3 to 2020 Q2
Collect secondary data on research conducted by grassroots organisation and research institutions in 12 mountain states on climate change, DRR, mountain livelihoods, gender | bar: 2017 Q3 to 2018 Q1
Capture and collate best pactices on climate chage, DRR, mountian liveihoods, gender from across 12 mountain states through state chapters | bar: 2017 Q3 to 2018 Q2
Research on gaps between centre and state policy and ground implementation on climate change, DRR, mountain livelihoods, gender | bar: 2018 Q1 to 2020 Q1
State of the Mountains Report (SoMR) | bar: 2018 Q2
Reference document in respect of mountain states when india submits its quinquennial report on SDGs of Rio+20 | bar: 2019 Q4
Research and collate a report examining state of progress on 17 Sustainable Development Goals (SDGs) in each mountain state | bar: 2019 Q1 to 2020 Q3
Objective 3: Build awareness and communicate sectorial learnings and best practices to all stakeholders and identify ways for upscaling across all mountain states.
Conduct Sustainable Mountain Development Summits (SMDS) in a different IHR state | bar: 2017 Q2; 2018 Q2; 2019 Q2; 2020 Q2
SMDS Proceedings | bar: 2017 Q4; 2018 Q4; 2019 Q4; 2020 Q4
Conduct Meet of Mountain States (MoMS) | bar: 2017 Q4; 2018 Q4; 2019 Q4; 2020 Q4
MoMS proceedings | bar: 2018 Q2; 2019 Q2; 2020 Q2
Create mountain monthly newsletter
Create mountain bulletin | bar: 2017 Q3; 2018 Q2; 2019 Q1; 2019 Q4; 2020 Q3
Create knowledge sharing platform - a database and interactve forum
Annual project status report | bar: 2017 Q4; 2018 Q4; 2019 Q4
Interim project status report | bar: 2018 Q4
Final Project Report | bar: 2020 Q4
Objective 4: Advocate for adoption of mountain specific policies and developmental frameworks in the Government of India (GoI) and Indian Himalayan States
Establish institutions to study and research mountain development policies
Meet of Mountain States | bar: 2017 Q4; 2018 Q4; 2019 Q4; 2020 Q4
Produce research and policy briefs
Partnership with Niti Aayog | bar: 2018 Q1 to 2020 Q4
Strenthen policy and practice on DRR in mountain states
Facilitate the work towards developing a legislature in Climate Change Act for the mountain states
Formulate State Action Plan for Climate Change (SAPCC)
Track progress of SDGs in IHR states